## Backend — RANK
Epic | User Story # | Task # | Epic Name | User Story | Activity | Deliverable | Dependent Task | Ext. Dependency | Int. Dependency | ETA
EP-RANK |  |  | Ranking Agent (Agent 5) — Backend
| US-RANK-BE-01 |  |  | As a recruiter I get one combined score per candidate that blends CV match and interview performance.
|  | EP-RANK-BE-001 |  |  | Composite scoring core | New module ranking_agent.py. Implement pure fn compute_composite(fit_percent, interview_score) returning {composite_score, score_breakdown {cv_match, interview, weights}}. Weights read from env RANK_CV_WEIGHT (default 0.4) and RANK_INTERVIEW_WEIGHT (default 0.6), normalised to sum 1.0. Clamp result 0-100. When interview_score is None (candidate never interviewed) score CV-only so half-scored candidates cannot outrank interviewed ones. No DB, no side effects. | — |  |  | 2h
|  | EP-RANK-BE-002 |  |  | Recommendation mapping | Pure fn recommend(composite_score, red_flags) -> strong_yes (>=80) / yes (>=65) / maybe (>=50) / no (else). When red_flags is non-empty, downgrade: return "review" if score>=70 else "no". Guard clause on empty input. | EP-RANK-BE-001 |  |  | 1h
|  | EP-RANK-BE-003 |  |  | Module self-test block | Add an if __name__ == "__main__" block exercising compute_composite happy path, the None-interview CV-only path, and recommend across strong_yes / review (with flag) / no — per repo convention that every module self-tests. No DB required to run. | EP-RANK-BE-002 |  |  | 0.5h
| US-RANK-BE-02 |  |  | As a recruiter the system persists a unified ranked shortlist I can pull per job.
|  | EP-RANK-BE-004 |  |  | Persist per-candidate ranking | Add collection helpers (_get_db/_candidates/_screened/_insights/_ranked) matching the lazy-singleton pattern in shortlisting_agent.py. Implement rank_candidate(cv_id): read fit_percent from candidates_info, interview_score from screened_candidates, red_flags/key_strengths from interview_insights; compute composite + recommendation; upsert a ranked_candidates doc {_id, jd_id, name/email/phone, composite_score, score_breakdown, recommendation, red_flags, key_strengths, interview_status, ranked_at}; mirror composite_score+recommendation onto candidates_info. Guard-clause return None on unknown cv_id. Idempotent. | EP-RANK-BE-001 |  |  | 3h
|  | EP-RANK-BE-005 |  |  | Ranked shortlist query | Implement rank_for_jd(jd_id, top_n=None) returning ranked_candidates for the job sorted by composite_score descending, each annotated with a 1-based rank field; top_n caps the list, omitting returns the full list. | EP-RANK-BE-004 |  |  | 2h
|  | EP-RANK-BE-006 |  |  | Ranked-candidates API endpoint | Add GET /ranked-candidates to app.py (query params jd_id, optional top_n, skip/limit pagination consistent with the existing /shortlisted-candidates endpoint). Add a RankedListResponse Pydantic model to schemas.py. Return ranked records highest-composite-first. | EP-RANK-BE-005 |  |  | 3h
| US-RANK-BE-03 |  |  | As a recruiter I can re-rank a job on demand after changing the scoring weights.
|  | EP-RANK-BE-007 |  |  | On-demand re-rank endpoint | Add POST /jobs/{jd_id}/rerank to app.py that recomputes every ranked_candidates record for the JD using the current env weights (PRD "re-ranking flow"); optionally accept {cv_weight, interview_weight} in the request body to override for that run. Returns the refreshed ranked shortlist. | EP-RANK-BE-004 |  |  | 2h

## Backend — PIPE
Epic | User Story # | Task # | Epic Name | User Story | Activity | Deliverable | Dependent Task | Ext. Dependency | Int. Dependency | ETA
EP-PIPE |  |  | Cohesive LangGraph Pipeline (Agents 2-5) — Backend
| US-PIPE-BE-01 |  |  | As the system, each candidate flows through one connected, checkpointed pipeline graph instead of separate scheduler steps.
|  | EP-PIPE-BE-001 |  |  | Define shared pipeline state | New module pipeline.py. Define PipelineState TypedDict: cv_id, jd_id, profile fields (name/email/phone/experience/education/raw_cv_text), fit_percent, call_id/transcript/summary/interview_score/call_category, booking_token/selected_slot/meet_link, composite_score/recommendation, stage/status. Must be JSON-serialisable so the checkpointer can persist it. | — |  |  | 3h
|  | EP-PIPE-BE-002 |  |  | Checkpointer + graph factory | Add create_pipeline_agent() that compiles an (initially empty) StateGraph over PipelineState with a SQLite checkpointer, falling back to InMemorySaver on failure — reuse the pattern from job_post.py:_build_checkpointer (separate sqlite file, e.g. pipeline_checkpoints.sqlite). | EP-PIPE-BE-001 |  |  | 2h
| US-PIPE-BE-02 |  |  | As the system, a new applicant is parsed and scored against their JD, then routed by CV fit.
|  | EP-PIPE-BE-003 |  |  | Parse CV node | Add parse_cv node wrapping parser_agent.process_cv(pdf_path, jd_id); populate the profile fields of PipelineState from the returned candidate dict. Node runs in the first invoke before any interrupt, so the temp PDF path is valid. Set entry point to parse_cv. | EP-PIPE-BE-002 |  |  | 3h
|  | EP-PIPE-BE-004 |  |  | Match node | Add match node wrapping shortlisting_agent._score_candidate_against_jd(candidate, jd_text) (load jd_text from job_descriptions by jd_id); write fit_percent into both PipelineState and candidates_info to keep the existing dashboards in sync. | EP-PIPE-BE-003 |  |  | 2h
|  | EP-PIPE-BE-005 |  |  | CV-threshold router + reject node | Add conditional edge route_after_match: fit_percent >= VOICE_CALL_THRESHOLD (env) routes to start_interview, otherwise to a terminal reject node that records status="rejected_cv" and ends. Read the threshold from env, no hardcode. | EP-PIPE-BE-004 |  |  | 2h
| US-PIPE-BE-03 |  |  | As the system, a qualified candidate is voice-interviewed and the call result resumes the pipeline.
|  | EP-PIPE-BE-006 |  |  | Interview node + interrupt | Add start_interview node: call _initiate_vapi_call(phone_e164), insert the screened_candidates row (status="calling") exactly as call_top_candidates does today, then interrupt() to suspend the graph until the Vapi webhook arrives. Highest-risk ticket (async interrupt/resume) — assign to strongest dev. | EP-PIPE-BE-005 |  |  | 4h
|  | EP-PIPE-BE-007 |  |  | Webhook resume wiring | Modify POST /voice/webhook in app.py to resolve cv_id via screened_candidates.call_id and resume the graph thread with Command(resume={transcript, summary, end_reason, duration}) instead of calling record_call_result directly. Guard unknown/duplicate call_id (no crash). No regression to the status="calling" insert. | EP-PIPE-BE-006 |  |  | 4h
|  | EP-PIPE-BE-008 |  |  | Interview scoring node | Add score_interview node (resume target): categorize_call, then _score_interview(transcript, summary, job_desc) and extract_interview_insights; persist interview_score, call_category and insights with parity to the current record_call_result behaviour. | EP-PIPE-BE-007 |  |  | 3h
|  | EP-PIPE-BE-009 |  |  | Interview-threshold router | Add route_after_interview: completed AND interview_score >= CALENDAR_THRESHOLD -> book; completed AND below -> rank; not-completed -> reject (keep the call_logs retry path compatible). All three branches reachable. | EP-PIPE-BE-008 |  |  | 2h
| US-PIPE-BE-04 |  |  | As the system, a strong interviewee is sent a slot picker and their selection resumes the pipeline.
|  | EP-PIPE-BE-010 |  |  | Booking node + interrupt | Add book node: call create_slot_picker_booking(candidate_doc, score) to email the picker link, then interrupt() to suspend until the candidate selects a slot. | EP-PIPE-BE-009 |  |  | 4h
|  | EP-PIPE-BE-011 |  |  | Slot-select resume + event node | Modify POST /api/booking/{token}/select in app.py to resolve cv_id via the pending_bookings token and resume the thread with Command(resume={selected_slot, meet_link}); add create_event node that records meet_link/selected_slot into state (preserve existing select_slot calendar-event behaviour). | EP-PIPE-BE-010 |  |  | 4h
| US-PIPE-BE-05 |  |  | As a recruiter, every candidate who completes the journey ends with a composite ranked record.
|  | EP-PIPE-BE-012 |  |  | Ranking terminal node | Add rank terminal node calling ranking_agent.rank_candidate(cv_id) then END. Both the booking path and the below-booking-threshold completed path converge here. Cross-epic dependency: requires EP-RANK-BE-004. | EP-PIPE-BE-011 |  | EP-RANK-BE-004 | 2h
| US-PIPE-BE-06 |  |  | As the system, the scheduler launches one pipeline run per applicant instead of running ingest/shortlist/call sequentially.
|  | EP-PIPE-BE-013 |  |  | Scheduler launches pipeline | Refactor _shortlist_loop (app.py:34) so it only detects new applicants (new Sheet rows / Drive file_ids, dedup via processed_applications) and launches or resumes one graph per candidate; stop calling shortlist_all_jobs / call_top_candidates directly — the graph now owns scoring and calling. | EP-PIPE-BE-012 |  |  | 4h
|  | EP-PIPE-BE-014 |  |  | End-to-end validation harness | Extend the test_booking_flow.py-style standalone harness to drive one fixture candidate from parse to a ranked_candidates record, simulating the Vapi webhook and slot-pick resumes; assert existing /candidates, /shortlisted-candidates, /screened_candidates endpoints still read the same collections. | EP-PIPE-BE-013 |  |  | 4h